Wirral Local Offer Steering Group

Minutes of Meeting held on 1st July 2014

Wallasey Town Hall 1.00 to 3.00pm

Present:  Peter Davies, Louise Reecejones, Kirsteen Sheppard, Debbie Marchant, Shirley Callahan, Tamsin Coates, Josh Humphries.

Chair: Peter Davies

Minutes: PD

1 Apologies  Karen Livesey, Lynn Loughran, Katy Coxhead,  Julie Hudson, Karen Ellis, Pauline Severs, Carolyn Duncan, Elaine Idris

2.  minutes last meeting 18-06-2014 passed.

Items discussed or for follow up:

- More in depth timeline for Local Offer preparation. Action – PD

- Discussion about commissioning of bases/special schools. This led on to how head teachers/schools/others can make comments about services delivered by LA (some services have budgets eroding).  This is big piece of work and will looked at in the autumn term. (includes Trip Advisor investigation work).

- Better Health and Social Care involvement needed, SC.

- Debate on the use of ‘School Offer’ labelling for schools web sites. Action: LR and SH/DM to follow up with Family Forum and Primary Heads Forum.

3.  IT platform, Community Action Wirral. Update from KS on design work with Family Forum parents. Discussed ‘wire frame’ needs to be in place before demonstration of web page. Charity/voluntary links need to be clear on site. Further work to be progressed on developing additional links for service/ team areas. KS has contacted Corporate IT for regulations and also to enquire about marketing. A request has gone to Phil Ward for a ‘marketing budget’. New project overview plan circulated (includes draft template).

4. Information/guidance. PD shared draft1 of Family Advice leaflet. Action: KS volunteered to adapt further and share with group for final approval/changes at next meeting. LO Framework and Guidance doc to be completed in Sept/October 2014.

5. Early Years, FE and Social Care engagement. List of authors needs to be built up - PD shared letters sent to Early Years providers and to LA service managers- which asks for these to contact KS. EY awareness sessions 14th July, 6-7pm and 23rd July (3 sessions). Venue PEC. PD/JH/LR to deliver.

6. Schools feedback from 26th June. Issues about the ‘School Offer (see above, 2). Issues about involvement in other strands.

7. Quality Assurance. PD has met with LR and TC. Due to demands on time this will be a task for Sept/Oct 2014.

8. AoB.

- Concerns that LO Steering Group will be over-ruled by LA Officers, TC. PD said he would raise this at SEND Overview Group.

- LR awareness raising on SEND reforms needed for councillors. (also for LA managers).

- Involvement of senior managers in the LO needed to help push progress. Action: PD asked to contact Claire Fish and Julia Hassall.

9. Date and time of next meeting 15th July 12.00 to 2.00 pm, Wallasey Town Hall